## Sheet1
Date | Time | Duration | Task Details | Task ID | Student Name
2024-02-21 | 11:00 | 1 hr | clean all the missing values from the raw data | #40 | Arnav Raviraj
2024-02-21 | 12:00 | 2 hrs | Find out how to implement GANS for our dataset | #45 | Vinay Chavhan
2024-02-21 | 16:30 | 1 hour | improve model performance on selected metrics | #31 | Adit Virkar
2024-02-21 | 9:00 | 1hr | creating initial neural net | #41 | Shivanjay Wagh
2024-02-21 | 22:00 | 1hr | creating initial neural net | #41 | Shivanjay Wagh
2024-02-22 | 10:00 | 1 hr | Find out how to implement GANS for our dataset | #45 | Vinay Chavhan
2024-02-22 | 17:00 | 1 hr | Find out how to implement GANS for our dataset | #45 | Vinay Chavhan
2024-02-22 | 19:00 | 1 hour | improve model performance on selected metrics | #31 | Adit Virkar
2024-02-22 | 23:00 | 1 hr | clean all the missing values from the raw data | #40 | Arnav Raviraj
2024-02-22 | 9:00 | 1hr | creating initial neural net | #41 | Shivanjay Wagh
2024-02-22 | 22:00 | 1hr | creating initial neural net | #41 | Shivanjay Wagh
2024-02-23 | 10:00 | 1 hr | clean all the missing values from the raw data | #40 | Arnav Raviraj
2024-02-23 | 17:00 | 1 hr | Find out how to implement GANS for our dataset | #45 | Vinay Chavhan
2024-02-23 | 19:30 | 1 hour | improve model performance on selected metrics | #31 | Adit Virkar
2024-02-23 | 19:30 | 1 hour | Create documentation and log the results | #37 | Adit Virkar
2024-02-23 | 9:00 | 1hr | creating initial neural net | #41 | Shivanjay Wagh
2024-02-23 | 22:00 | 1hr | creating initial neural net | #41 | Shivanjay Wagh
2024-02-24 | 15:00 | 2 hr | Find out how to implement GANS for our dataset | #45 | Vinay Chavhan
2024-02-24 | 17:00 | 1 hr | create the generative GANBased model | #46 | Vinay Chavhan
2024-02-24 | 1 :00 P.M | 1.5 hr | Find out the correlation between features | #38 | Arnav Raviraj
2024-02-24 | 2:30 P.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-02-24 | 18:30 | 1 hour | improve model performance on selected metrics | #31 | Adit Virkar
2024-02-24 | 18:30 | 1 hour | Create documentation and log the results | #37 | Adit Virkar
2024-02-24 | 9:00 | 1hr | training neural net | #42 | Shivanjay Wagh
2024-02-24 | 22:00 | 1hr | training neural net | #42 | Shivanjay Wagh
2024-02-25 | 10:00 | 3 hr | create the generative GANBased model | #46 | Vinay Chavhan
2024-02-25 | 14:00 | 1 hr | Log the work and create documentation for it | #49 | Vinay Chavhan
2024-02-25 | 19:00 | 1 hour | Do hyper parameter tuning | #36 | Adit Virkar
2024-02-25 | 10:00 P.M | 1.5 hr | Find out the correlation between features | #38 | Arnav Raviraj
2024-02-25 | 11:30 P.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-02-25 | 9:00 | 1hr | training neural net | #42 | Shivanjay Wagh
2024-02-25 | 22:00 | 1hr | training neural net | #42 | Shivanjay Wagh
2024-02-26 | 9:00 | 2 hr | create the generative GANBased model | #46 | Vinay Chavhan
2024-02-26 | 11:00 | 1 hr | Log the work and create documentation for it | #49 | Vinay Chavhan
2024-02-26 | 8:00 P.M | 1 hr | Find out the correlation between features | #38 | Arnav Raviraj
2024-02-26 | 9:00 P.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-02-26 | 21:30 | 1 hour | Do hyper parameter tuning | #36 | Adit Virkar
2024-02-26 | 9:00 | 1hr | training neural net | #42 | Shivanjay Wagh
2024-02-26 | 22:00 | 1hr | training neural net | #42 | Shivanjay Wagh
2024-02-27 | 10:00 | 2 hrs | create the generative GANBased model | #46 | Vinay Chavhan
2024-02-27 | 12:00 | 1 hr | Log the work and create documentation for it | #49 | Vinay Chavhan
2024-02-27 | 20:00 | 1 hour | Do hyper parameter tuning | #36 | Adit Virkar
2024-02-27 | 20:00 | 1 hour | Create documentation and log the results | #37 | Adit Virkar
2024-02-27 | 10:00 P.M | 1 hr | Find out the correlation between features | #38 | Arnav Raviraj
2024-02-27 | 11:00 P.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-02-27 | 9:00 | 1hr | Finding the correct number of hidden layers | #43 | Shivanjay Wagh
2024-02-27 | 22:00 | 1hr | Finding the correct number of hidden layers | #43 | Shivanjay Wagh
2024-02-28 | 11:00 | 1 hr | improving the accuracy of Boosting Models | #44 | Vinay Chavhan
2024-02-28 | 12:00 | 30 mins | Log the work and create documentation for it | #46 | Vinay Chavhan
2024-02-28 | 19:00 | 2 hours | Do hyper parameter tuning | #36 | Adit Virkar
2024-02-28 | 19:00 | 2 hours | Create documentation and log the results | #37 | Adit Virkar
2024-02-28 | 11:00 P.M | 30 mins | Find out the correlation between features | #38 | Arnav Raviraj
2024-02-28 | 11:30 P.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-02-28 | 9:00 | 1hr | Finding the correct number of hidden layers | #43 | Shivanjay Wagh
2024-02-28 | 22:00 | 30 mins | Finding the correct number of hidden layers | #43 | Shivanjay Wagh
2024-02-29 | 9:00 | 1 hour | Do hyper parameter tuning | #36 | Adit Virkar
2024-02-29 | 9:00 | 1 hour | Create documentation and log the results | #37 | Adit Virkar
2024-02-29 | 12:00 P.M | 1 hr | Find out the correlation between features | #38 | Arnav Raviraj
2024-02-29 | 1:00 P.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-02-29 | 17:00 | 2 hrs | improving the accuracy of Boosting Models | #44 | Vinay Chavhan
2024-02-29 | 19:00 | 30 mins | Log the work and create documentation for it | #46 | Vinay Chavhan
2024-02-29 | 9:00 | 1hr | Finding the correct number of hidden layers | #43 | Shivanjay Wagh
2024-02-29 | 22:00 | 1hr | Finding the correct number of hidden layers | #43 | Shivanjay Wagh
2024-03-01 | 10:00 A.M | 1 hr | Find out the correlation between features | #38 | Arnav Raviraj
2024-03-01 | 11:00 A.M | 30 mins | Log the work and create new documentation for it | #50 | Arnav Raviraj
2024-03-01 | 11:00 | 2 hrs | improving the accuracy of Boosting Models | #44 | Vinay Chavhan
2024-03-01 | 12:00 | 20 mins | Log the work and create documentation for it | #46 | Vinay Chavhan
2024-03-01 | 13:00 | 1 hour | Do hyper parameter tuning | #36 | Adit Virkar
2024-03-01 | 13:00 | 1 hour | Create documentation and log the results | #37 | Adit Virkar
2024-03-01 | 9:00 | 1hr | Obtain the final accuracy of the model | #48 | Shivanjay Wagh
2024-03-01 | 10:00 | 40 mins | Obtain the final accuracy of the model | #48 | Shivanjay Wagh